SOESD Implementation Oversight Committee (SB 290)

WORK PLAN

Revised 11/13/13

| Outcome | Activity/Task | Needed Resources | Person(s) Responsible | Timeline | Notes |
| --- | --- | --- | --- | --- | --- |
| TRAINING: Training all staff and evaluators on the local evaluation and support system | Review standards & align the essential functions of all licensed & administrative job descriptions with the InTASC & ISLLC standards, respectively | Listing of current job positions Copies of current job descriptions Feedback about the Standards activities & directions InTASC Standards Analysis Chart ISLLC Standards Analysis Chart | Program administrators All licensed staff | Spring 2013 |  |
|  | Overview of the evaluation system, including purpose, components, timelines, & roles/responsibilities | Evidence Binders w/ pocket dividers Background information (including standards, rubrics, Running Record of Evidence form) | Sandra Marian | August 27, 2013 |  |
|  | Introduction to multiple measures/types of evidence (including observations) | Activity #1 Gathering Evidence | Program Administrators All licensed staff | August 27, 2013 |  |
|  | Introduction to SL&G goals Preliminary program goal setting | Activity #2 Setting Goals | Program Administrators All licensed staff All classified staff | August 27, 2013 |  |
|  | Ongoing discussion re: implementation of evaluation system |  | Program Administrators All licensed staff | Regularly scheduled staff meetings |  |
|  | Planning, tracking, and documenting elements and timelines of teacher and administrator evaluations | Supervision Summary forms | Program Administrators | Per scheduled timelines |  |

| Outcome | Activity/Task | Needed Resources | Person(s) Responsible | Timeline | Notes |
| --- | --- | --- | --- | --- | --- |
| TRAINING: Training to ensure inter-rater reliability | Develop operational definitions for standards and rubrics which are clear, simple, precise, and measurable |  |  | October 21 IOC meeting | Use system as is Develop a feedback form for each program re: definitions (standards & rubrics), rubrics, and guiding questions |
|  | Provide training for evaluators regarding rubrics, including group practice calibration exercises for all raters within the same category of job positions (that is, viewing a sample performance, rating it individually first, then together with the group) |  | Kaye & Scott-sample performance videos | By November 6 Administrative Team training: November 12-calibration re: teachers December 10-calibration re: other licensed categories January 14 February 11 March 11 April 16 | There are teacher effectiveness videos available for this purpose (e.g., learn 360 & Teachscape). Is there one from Salem-Keizer, Chalkboard, or through OEA? There was also inter-rater reliability training presented to Salem-Keizer by Chalkboard. |
|  | Develop model (or sample) activities to demonstrate differentiated ratings in selected standard/objective areas |  |  |  | Need to develop models/ samples for each score for each indicator. This will take all year; we will develop a training library over time |
|  | Develop additional “Guiding Questions” for other SOESD job position categories not currently addressed in the adopted Salem-Keizer Legends (Licensed Staff Assessment and Evaluation) Rubric |  |  | Wait on this | Do we need separate Guiding Questions for Tech & Media job positions? Salem-Keizer has developed an additional rubric for SLPs and working on ones for other specialists (e.g., OTs/PTs). |
|  | Tie these activities to established professional standards (such as the NASP standards) and competencies (such as the Autism Spectrum Disorder Specialist competencies) |  |  |  | What other professional standards or competencies should be considered? Use other standards/competencies as evidence. |
|  | Develop sample evaluation reports |  |  |  | Need to figure out how to consider all scores in calculation of summative scores. We’ll need different examples for each licensed category. |
|  | Define guidelines and parameters for observations, including types of observations, frequency, duration, types of activities appropriate for observation, and who will be the observer |  |  |  | At least 2 formal observations per evaluation cycle. Determine parameters later, as they may be different for different programs. Develop mini-checklists for drop-in observations. Do we need to score last year’s observation if it is included in this year’s evaluation? |
|  | Clearly define the process for individual follow-up, including how and when to provide feedback, how to incorporate observation findings into the summative evaluation and the weighting of observations into summative evaluation scores |  |  |  | Need to score evidence and figure out how to combine scores for each standard. We recommend a chance to resubmit evidence for a better score. What is the conversation at the mid-year review? How do we document the mid-year review? This could start as a self-assessment by the person being evaluated. Perhaps we could use the Guiding Questions for the (1) conversation (2) documenta-tion, and (3) score. |
|  | Compare summative evaluation scores of probationary v. contract teachers |  |  | March 17, 2014 IOC meeting | What is the purpose of comparing scores of probationary v. contract teachers? Compare scores under the previous system to scores under SB 290 to establish a baseline. Compare scores across SOESD evaluators. Does “meets” now have higher expectations (we’ve been told to expect “2”s)? |
|  | Consider ways to compare SOESD’s overall agency summative evaluation score with those of other ESDs with similar job position to provide additional inter-rater reliability data |  |  |  | Will it matter which rubric was used? Set up an agreement with other ESDs ahead of time (perhaps 3-4 ESDs which participated in the ESD Work Group). |

| Outcome | Activity/Task | Needed Resources | Person(s) Responsible | Timeline | Notes |
| --- | --- | --- | --- | --- | --- |
| MONITORING PROGRESS: | Establish Implementation Oversight Committee |  |  | October 9, 2013 |  |
|  | Provide oversight of the implementation of and training regarding SOESD’s teacher and administrator evaluation system |  |  |  |  |
|  | Clearly define the process for department and agency level follow-up and system evaluation, including who will compile program-level summaries and averages and what process will be in place to analyze and review data across SOESD and departments over time |  |  |  |  |
|  | Establish accountability measures to make sure that each administrator implements the evaluation system, including -Meeting with Directors to set department and professional goals -Setting the evaluation schedule (that is, planning the Supervision Summary) -Receiving feedback from their supervisors regarding their conduct of observations and evaluations -Meeting periodically to review goals and monitor the Supervision Summary |  |  |  |  |
|  | Provide agency-wide oversight regarding the fidelity of the implementation of the evaluation system |  |  |  |  |
|  | Collect feedback from teachers and administrators about their experiences as evaluators and those being evaluated (examples of feedback include using Survey Monkey) |  |  |  |  |
|  | Collect data re: fidelity of implementation and inter-rater reliability (see section above regarding inter-rater reliability) |  |  |  |  |
|  | Collect data re: professional goals and student learning & growth goals |  |  |  |  |
|  | Establish benchmarks for evaluation scores (an example follows) -100% SOESD staff will have summative evaluation scores of 3.0 or higher |  |  |  |  |
|  | Collect data by program/department and for the agency as a whole |  |  |  |  |
|  | Analyze all scores below 3.0 -Do the scores suggest a lack of fidelity of implementation of the evaluation system? -Do the scores indicate problems with inter-rater reliability? -Do the scores represent inadequate performance by staff? -Do the scores identify specific areas of concern and needed professional development? |  |  |  |  |
|  | Compare scores to those of other ESD (both ESD-wide and to subgroups of teachers and administrators) |  |  |  |  |

| Outcome | Activity/Task | Needed Resources | Person(s) Responsible | Timeline | Notes |
| --- | --- | --- | --- | --- | --- |
| REFINING THE EVALUATION & SUPPORT SYSTEM: | Make recommendations for adjustments in the evaluation system |  |  |  |  |
|  | Answer this bottom line question: Does the system fairly assess the job performance of SOESD staff? |  |  |  |  |