SOESD Teacher and Administrator Evaluation & Support System (SB 290) Planning Team

WORK SCOPE

| Task | Timeline | Work Scope | Outcome |
| --- | --- | --- | --- |
| Nominate a Committee | December 2012 to January 2013 | Ask for teacher and administrator representatives on the planning team to represent all SOESD departments and programs | Committee membership involves teachers, administrators, and bargaining representatives |
| Introduction to SB 290 | February 7, 2013 | Attend SB 290 overview presentation by Kathy McCollum at Special Education Administrators meeting | Basic understanding of requirements of SB 290 |
| Overview of Current Evaluation System | March 5, 2013 | Review components of current SOESD teacher and administrator evaluation system | Knowledge of current system |
| Select Standards of Professional Practice | March 5, 2013 | Adopt InTASC (Interstate Teacher Assessment and Support Consortium) Model Core Teaching Standards or develop one of our own; Adopt ISLLC (Interstate School Leaders Licensure Consortium) Standards or develop one of our own | Selection of: - InTASC Teaching Standards - ISLLC Administrator Standards |
| Select Evaluation Rubrics | March 5, 2013 | Adopt one of 4 “approved” teacher evaluation rubrics, modify, or develop one: - Danielson - Marshal - Salem-Keizer - Marzano Adopt one of 3 “approved” administrator evaluation rubrics, modify, or develop one: - Salem-Keizer - Oregon Educational Leadership - Pendleton | Selection of: - Salem-Keizer Legends Rubric - Oregon Educational Leader/Administrator Rubric |
| Identify Differentiated Performance Levels | March 15, 2013 | Adopt performance levels of selected rubric(s) or develop our own descriptors (Ratings=1-4) | Adopted these performance levels: 1=Does Not Meet Standard 2=Basic Knowledge of Standard 3=Proficient Application of Standard 4=Exceeds Standard |

| Task | Timeline | Work Scope | Outcome |
| --- | --- | --- | --- |
| Review Multiple Measures | March 15, 2013 | Define & quantify measures, including: - Professional Practice - Professional Responsibilities - Student Learning & Growth | Brainstormed examples of evidence-based measures of teacher and administrator performance and effectiveness; Considered how to measure impact on Student Learning and Growth by SOESD job positions not directly related to student instruction |
| Describe Evaluation & Professional Growth Cycle | April 8, 2013 | Describe elements and timelines of a cycle of continuous professional growth and learning that includes these processes: - Self-Reflection - Goal Setting - Observation/Collection of Evidence - Formative Assessment/Evaluation - Summative Evaluation | Current SOESD evaluation system incorporates these processes with exception of Student Learning & Growth (SL&G) Goals; Proposed mechanism for addressing SL&G goals as they apply to different categories of licensed and administrative staff |
| Link Aligned Professional Learning to Evaluation Cycle | April 8, 2013 | Describe how evaluation system will be aligned with opportunities for professional growth | Current SOESD evaluation system incorporates opportunities for professional growth; Suggested emphasis on program goals, which will target professional development on program-wide basis, including identification of needed inservice training |
| Review Proposed Components of Evaluation System | April 25, 2013 | Review all proposed components of evaluation system for internal consistency and application to SOESD licensed and administrative job positions | Revised draft documents |
| Review Feedback about Standards | April 25, 2013 | Review feedback from programs regarding alignment of adopted standards to job positions | InTASC Standards Analysis Chart ISLLC Standards Analysis Chart |
| Develop Implementation Plan | May 1, 2103 | Develop plan for implementing the evaluation & support system, including: - Training all staff & evaluators - Monitoring progress and refining the evaluation & support system | Outline of work to be completed by July 1, during Summer 2013, and during 2013-2014 school year |

| Task | Timeline | Work Scope | Outcome |
| --- | --- | --- | --- |
| Plan Board Presentation | May 9, 2013 | Develop proposal to SOESD board of directors and determine which documents to provide, including Assurances and background information | Board presentation outline; Scheduled 4 planning team meetings during July & August 2013 |
| Secure Board Approval | May 15, 2013 | Present proposal to SOESD board of directors | Board presentation |
| Respond to Board Feedback | May 29, 2013 | Respond to board’s feedback; revise documents per feedback; Begin work on What Needs to Be Done by July 1 | Revised documents |
| Report back to Board with Revisions | June 19, 2013 | Re-submit recommendations per board revisions | Final board approval |
| What Needs to Be Done | June 24, 2013 | Complete work on What Needs to Be Done chart by July 1 | Defined terms (standards & rubrics); Suggested evidence for teachers and administrators who are not involved in direct instruction; Summer Work Plan |
| Submit Assurances Template | July 1, 2013 | Submit Assurances to ODE | Signed and emailed Assurances and attachment |
| What Needs to Be Done | July 8, 2013 July 19, 2013 August 1, 2013 | Complete work on What Needs to Be Done chart during Summer 2013 | Guiding Questions and Evidence for other categories of teachers; Revised evaluation forms; August inservice planned; Implementation Oversight Committee established |